## Sheet1
Drop-Kick Picks Schedule
Task \ Week | Assignee | 2018-10-06 | 2018-10-13 | 2018-10-20 | 2018-10-27
Week #1
Application Overview | Rod
Schedule | Rod
Breakdown of roles by group member | Randy
Screenshot of Project Management Board (initial) | Rod
Detailed screen-by-screen design layout | Randy
Front End - User Authentication (Passport) | Rod
Week #2
Functioning minimal viable product | Both
5-7 min presentation | Both
Updated screenshot of Project Management Board | Rod
Back End - Mongo/Mongooes ODM | Rod
Front End - React/JSX/Bootstrap/Styling | Randy
Routing | Randy
API - Get Data for Games and Scores | Rndy
Week #3
Significantly more polished version of the app | Both
Summary of significant issues faced t date and their resolution
Provide a detailed description of each person's contributions
Detailed plan that describes remaining efforts
Week #4
Heroku Implementation
Presentation Slides
Final Presentation & Demo